## Group Details
EPM 1173_4/Spring 2023
Group 7
Name | Student ID
Nikesh Pathak | c0906596
Maurvi Shah | c0897184
Pradip Shrestha | c0899894
Paulina Jaramillo | c0897079
Rojohn Shrestha | c0898077

## Task_Table1
Name | Duration | Start_Date | Finish_Date | Predecessors | Percent_Complete | Status | Baseline_Start | Baseline_Finish | Baseline_Duration | Start_Variance | Finish_Variance | Fixed_Cost | Cost | Baseline_Cost | Cost_Variance | Actual_Cost | Remaining_Cost
Wards | 190 days | 2023 June 01 8:00 AM | 2024 February 21 5:00 PM |  | 0.25 | 2 | 2023 June 01 8:00 AM | 2024 February 12 5:00 PM | 183 days | 0d | 7d | 0 | 337072 | 214392 | 122680 | 92560 | 244512
Emergency Ward | 46 days | 2023 June 01 8:00 AM | 2023 August 03 5:00 PM |  | 1 | 0 | 2023 June 01 8:00 AM | 2023 July 25 5:00 PM | 39 days | 0d | 7d | 0 | 128880 | 18400 | 110480 | 63880 | 65000
Create Patient Triage Station | 14 days | 2023 June 01 8:00 AM | 2023 June 20 5:00 PM |  | 1 | 0 | 2023 June 01 8:00 AM | 2023 June 16 5:00 PM | 12 days | 0d | 2d | 0 | 42040 | 6720 | 35320 | 22040 | 20000
Set-up Ward | 12 days | 2023 June 20 5:00 PM | 2023 July 06 5:00 PM | 3 | 1 | 0 | 2023 June 16 5:00 PM | 2023 June 30 5:00 PM | 10 days | 2d | 4d | 0 | 69720 | 5600 | 64120 | 33720 | 36000
Set-up Nurses Station | 11 days | 2023 July 06 5:00 PM | 2023 July 21 5:00 PM | 4 | 1 | 0 | 2023 June 30 5:00 PM | 2023 July 13 5:00 PM | 9 days | 4d | 6d | 0 | 3520 | 2880 | 640 | 3520 | 0
Furnish Ward | 9 days | 2023 July 24 8:00 AM | 2023 August 03 5:00 PM | 5 | 1 | 0 | 2023 July 14 8:00 AM | 2023 July 25 5:00 PM | 8 days | 6d | 7d | 0 | 13600 | 3200 | 10400 | 4600 | 9000
Inspection approved | 0 days | 2023 August 03 5:00 PM | 2023 August 03 5:00 PM | 6 | 1 | 0 | 2023 July 25 5:00 PM | 2023 July 25 5:00 PM | 0 days | 7d | 7d | 0 | 0 | 0 | 0 | 0 | 0
ICU | 33 days | 2023 August 04 8:00 AM | 2023 September 19 5:00 PM |  | 2.9999999999999999E-2 | 2 | 2023 July 26 8:00 AM | 2023 September 08 5:00 PM | 33 days | 7d | 7d | 0 | 28800 | 20800 | 8000 | 540 | 28260
Set-up Ward | 18 days | 2023 August 04 8:00 AM | 2023 August 29 5:00 PM | 7 | 5.0000000000000003E-2 | 2 | 2023 July 26 8:00 AM | 2023 August 18 5:00 PM | 18 days | 7d | 7d | 0 | 18800 | 10800 | 8000 | 540 | 18260
Set-up Nurses Station | 10 days | 2023 August 30 8:00 AM | 2023 September 12 5:00 PM | 9 | 0 | 3 | 2023 August 21 8:00 AM | 2023 September 01 5:00 PM | 10 days | 7d | 7d | 0 | 8000 | 8000 | 0 | 0 | 8000
Furnish Ward | 5 days | 2023 September 13 8:00 AM | 2023 September 19 5:00 PM | 10 | 0 | 3 | 2023 September 04 8:00 AM | 2023 September 08 5:00 PM | 5 days | 7d | 7d | 0 | 2000 | 2000 | 0 | 0 | 2000
Medicine Ward | 28 days | 2023 September 20 8:00 AM | 2023 October 27 5:00 PM |  | 0 | 3 | 2023 September 11 8:00 AM | 2023 October 18 5:00 PM | 28 days | 7d | 7d | 0 | 12512 | 12512 | 0 | 0 | 12512
Set-up Ward | 12 days | 2023 September 20 8:00 AM | 2023 October 05 5:00 PM | 11 | 0 | 3 | 2023 September 11 8:00 AM | 2023 September 26 5:00 PM | 12 days | 7d | 7d | 0 | 6912 | 6912 | 0 | 0 | 6912
Set-up Nurses Station | 10 days | 2023 October 06 8:00 AM | 2023 October 19 5:00 PM | 13 | 0 | 3 | 2023 September 27 8:00 AM | 2023 October 10 5:00 PM | 10 days | 7d | 7d | 0 | 3200 | 3200 | 0 | 0 | 3200
Furnish Ward | 6 days | 2023 October 20 8:00 AM | 2023 October 27 5:00 PM | 14 | 0 | 3 | 2023 October 11 8:00 AM | 2023 October 18 5:00 PM | 6 days | 7d | 7d | 0 | 2400.0000000000005 | 2400.0000000000005 | 0 | 0 | 2400.0000000000005
General Ward | 30 days | 2023 October 30 8:00 AM | 2023 December 08 5:00 PM |  | 0 | 3 | 2023 October 19 8:00 AM | 2023 November 29 5:00 PM | 30 days | 7d | 7d | 0 | 17440 | 17440 | 0 | 0 | 17440
Set-up Ward | 12 days | 2023 October 30 8:00 AM | 2023 November 14 5:00 PM | 15 | 0 | 3 | 2023 October 19 8:00 AM | 2023 November 03 5:00 PM | 12 days | 7d | 7d | 0 | 11040 | 11040 | 0 | 0 | 11040
Set-up Nurses Station | 10 days | 2023 November 15 8:00 AM | 2023 November 28 5:00 PM | 17 | 0 | 3 | 2023 November 06 8:00 AM | 2023 November 17 5:00 PM | 10 days | 7d | 7d | 0 | 3200 | 3200 | 0 | 0 | 3200
Furnish Ward | 8 days | 2023 November 29 8:00 AM | 2023 December 08 5:00 PM | 18 | 0 | 3 | 2023 November 20 8:00 AM | 2023 November 29 5:00 PM | 8 days | 7d | 7d | 0 | 3200 | 3200 | 0 | 0 | 3200
Orthopedic Ward | 27 days | 2023 December 11 8:00 AM | 2024 January 16 5:00 PM |  | 0 | 3 | 2023 November 30 8:00 AM | 2024 January 05 5:00 PM | 27 days | 7d | 7d | 0 | 21360 | 21360 | 0 | 0 | 21360
Set-up Ward | 12 days | 2023 December 11 8:00 AM | 2023 December 26 5:00 PM | 19 | 0 | 3 | 2023 November 30 8:00 AM | 2023 December 15 5:00 PM | 12 days | 7d | 7d | 0 | 11040 | 11040 | 0 | 0 | 11040
Set-up Nurses Station | 9 days | 2023 December 27 8:00 AM | 2024 January 08 5:00 PM | 21 | 0 | 3 | 2023 December 18 8:00 AM | 2023 December 28 5:00 PM | 9 days | 7d | 7d | 0 | 7920 | 7920 | 0 | 0 | 7920
Furnish Ward | 6 days | 2024 January 09 8:00 AM | 2024 January 16 5:00 PM | 22 | 0 | 3 | 2023 December 29 8:00 AM | 2024 January 05 5:00 PM | 6 days | 7d | 7d | 0 | 2400.0000000000005 | 2400.0000000000005 | 0 | 0 | 2400.0000000000005
Paediatric Ward | 26 days | 2024 January 17 8:00 AM | 2024 February 21 5:00 PM |  | 0 | 3 | 2024 January 08 8:00 AM | 2024 February 12 5:00 PM | 26 days | 7d | 7d | 0 | 14080 | 14080 | 0 | 0 | 14080
Set-up Ward | 12 days | 2024 January 17 8:00 AM | 2024 February 01 5:00 PM | 23 | 0 | 3 | 2024 January 08 8:00 AM | 2024 January 23 5:00 PM | 12 days | 7d | 7d | 0 | 7200 | 7200 | 0 | 0 | 7200
Set-up Nurses Station | 8 days | 2024 February 02 8:00 AM | 2024 February 13 5:00 PM | 25 | 0 | 3 | 2024 January 24 8:00 AM | 2024 February 02 5:00 PM | 8 days | 7d | 7d | 0 | 2560.0000000000005 | 2560.0000000000005 | 0 | 0 | 2560.0000000000005
Furnish Ward | 6 days | 2024 February 14 8:00 AM | 2024 February 21 5:00 PM | 26 | 0 | 3 | 2024 February 05 8:00 AM | 2024 February 12 5:00 PM | 6 days | 7d | 7d | 0 | 4320 | 4320 | 0 | 0 | 4320
Final Inspection | 0 days | 2024 February 21 5:00 PM | 2024 February 21 5:00 PM | 27 | 0 | 3 | 2024 February 12 5:00 PM | 2024 February 12 5:00 PM | 0 days | 7d | 7d | 0 | 0 | 0 | 0 | 0 | 0
Speciality Rooms | 98 days | 2023 June 01 8:00 AM | 2023 October 16 5:00 PM |  | 0.57999999999999996 | 1 | 2023 June 01 8:00 AM | 2023 October 06 5:00 PM | 92 days | 0d | 6d | 0 | 59320 | 55960 | 3360 | 31440 | 27880
X-ray Room | 30 days | 2023 June 01 8:00 AM | 2023 July 12 5:00 PM |  | 1 | 0 | 2023 June 01 8:00 AM | 2023 July 06 5:00 PM | 26 days | 0d | 4d | 0 | 19200.000000000004 | 16720 | 2480.0000000000023 | 19200.000000000004 | 0
Set up Room | 16 days | 2023 June 01 8:00 AM | 2023 June 22 5:00 PM |  | 1 | 0 | 2023 June 01 8:00 AM | 2023 June 20 5:00 PM | 14 days | 0d | 2d | 0 | 14720.000000000002 | 12880 | 1840.0000000000023 | 14720.000000000002 | 0
Install Equipment | 14 days | 2023 June 23 8:00 AM | 2023 July 12 5:00 PM | 31 | 1 | 0 | 2023 June 21 8:00 AM | 2023 July 06 5:00 PM | 12 days | 2d | 4d | 0 | 4480 | 3840 | 640 | 4480 | 0
CT Scan Room | 27 days | 2023 July 13 8:00 AM | 2023 August 18 5:00 PM |  | 1 | 0 | 2023 July 07 8:00 AM | 2023 August 10 5:00 PM | 25 days | 4d | 6d | 0 | 12240 | 11360 | 880 | 12240 | 0
Set up Room | 15 days | 2023 July 13 8:00 AM | 2023 August 02 5:00 PM | 32 | 1 | 0 | 2023 July 07 8:00 AM | 2023 July 26 5:00 PM | 14 days | 4d | 5d | 0 | 8400 | 7840 | 560 | 8400 | 0
Install Equipment | 12 days | 2023 August 03 8:00 AM | 2023 August 18 5:00 PM | 34 | 1 | 0 | 2023 July 27 8:00 AM | 2023 August 10 5:00 PM | 11 days | 5d | 6d | 0 | 3840 | 3520 | 320 | 3840 | 0
Blood Works Lab | 19 days | 2023 August 21 8:00 AM | 2023 September 14 5:00 PM |  | 0 | 3 | 2023 August 11 8:00 AM | 2023 September 06 5:00 PM | 19 days | 6d | 6d | 0 | 13480 | 13480 | 0 | 0 | 13480
Set up Room | 10 days | 2023 August 21 8:00 AM | 2023 September 01 5:00 PM | 35 | 0 | 3 | 2023 August 11 8:00 AM | 2023 August 24 5:00 PM | 10 days | 6d | 6d | 0 | 7000 | 7000 | 0 | 0 | 7000
Install Equipment | 9 days | 2023 September 04 8:00 AM | 2023 September 14 5:00 PM | 37 | 0 | 3 | 2023 August 25 8:00 AM | 2023 September 06 5:00 PM | 9 days | 6d | 6d | 0 | 6480 | 6480 | 0 | 0 | 6480
ECG | 22 days | 2023 September 15 8:00 AM | 2023 October 16 5:00 PM |  | 0 | 3 | 2023 September 07 8:00 AM | 2023 October 06 5:00 PM | 22 days | 6d | 6d | 0 | 14400 | 14400 | 0 | 0 | 14400
Set up Room | 12 days | 2023 September 15 8:00 AM | 2023 October 02 5:00 PM | 38 | 0 | 3 | 2023 September 07 8:00 AM | 2023 September 22 5:00 PM | 12 days | 6d | 6d | 0 | 7200 | 7200 | 0 | 0 | 7200
Install Equipment | 10 days | 2023 October 03 8:00 AM | 2023 October 16 5:00 PM | 40 | 0 | 3 | 2023 September 25 8:00 AM | 2023 October 06 5:00 PM | 10 days | 6d | 6d | 0 | 7200 | 7200 | 0 | 0 | 7200
Final inspection | 0 days | 2023 October 16 5:00 PM | 2023 October 16 5:00 PM | 41 | 0 | 3 | 2023 October 06 5:00 PM | 2023 October 06 5:00 PM | 0 days | 6d | 6d | 0 | 0 | 0 | 0 | 0 | 0
IT Systems | 98 days | 2023 October 17 8:00 AM | 2024 February 29 5:00 PM |  | 0 | 3 | 2023 October 09 8:00 AM | 2024 February 21 5:00 PM | 98 days | 6d | 6d | 0 | 89880 | 89880 | 0 | 0 | 89880
Server room + Networking | 27 days | 2023 October 17 8:00 AM | 2023 November 22 5:00 PM |  | 0 | 3 | 2023 October 09 8:00 AM | 2023 November 14 5:00 PM | 27 days | 6d | 6d | 0 | 22400 | 22400 | 0 | 0 | 22400
Install Network | 12 days | 2023 October 17 8:00 AM | 2023 November 01 5:00 PM | 41 | 0 | 3 | 2023 October 09 8:00 AM | 2023 October 24 5:00 PM | 12 days | 6d | 6d | 0 | 11600 | 11600 | 0 | 0 | 11600
Install Hardware | 10 days | 2023 November 02 8:00 AM | 2023 November 15 5:00 PM | 45 | 0 | 3 | 2023 October 25 8:00 AM | 2023 November 07 5:00 PM | 10 days | 6d | 6d | 0 | 5600 | 5600 | 0 | 0 | 5600
Install Software | 5 days | 2023 November 16 8:00 AM | 2023 November 22 5:00 PM | 46 | 0 | 3 | 2023 November 08 8:00 AM | 2023 November 14 5:00 PM | 5 days | 6d | 6d | 0 | 5200 | 5200 | 0 | 0 | 5200
Computers | 14 days | 2023 November 23 8:00 AM | 2023 December 12 5:00 PM |  | 0 | 3 | 2023 November 15 8:00 AM | 2023 December 04 5:00 PM | 14 days | 6d | 6d | 0 | 26440 | 26440 | 0 | 0 | 26440
Install Computers | 10 days | 2023 November 23 8:00 AM | 2023 December 06 5:00 PM | 47 | 0 | 3 | 2023 November 15 8:00 AM | 2023 November 28 5:00 PM | 10 days | 6d | 6d | 0 | 15200 | 15200 | 0 | 0 | 15200
Install OS | 4 days | 2023 December 07 8:00 AM | 2023 December 12 5:00 PM | 49 | 0 | 3 | 2023 November 29 8:00 AM | 2023 December 04 5:00 PM | 4 days | 6d | 6d | 0 | 11240 | 11240 | 0 | 0 | 11240
Communications Systems | 32 days | 2023 December 13 8:00 AM | 2024 January 25 5:00 PM |  | 0 | 3 | 2023 December 05 8:00 AM | 2024 January 17 5:00 PM | 32 days | 6d | 6d | 0 | 21120 | 21120 | 0 | 0 | 21120
Install telephones | 8 days | 2023 December 13 8:00 AM | 2023 December 22 5:00 PM | 50 | 0 | 3 | 2023 December 05 8:00 AM | 2023 December 14 5:00 PM | 8 days | 6d | 6d | 0 | 4480 | 4480 | 0 | 0 | 4480
Install Public Address system | 9 days | 2023 December 25 8:00 AM | 2024 January 04 5:00 PM | 52 | 0 | 3 | 2023 December 15 8:00 AM | 2023 December 27 5:00 PM | 9 days | 6d | 6d | 0 | 5040.0000000000009 | 5040.0000000000009 | 0 | 0 | 5040.0000000000009
Connect phones | 7 days | 2024 January 05 8:00 AM | 2024 January 15 5:00 PM | 53 | 0 | 3 | 2023 December 28 8:00 AM | 2024 January 05 5:00 PM | 7 days | 6d | 6d | 0 | 3920 | 3920 | 0 | 0 | 3920
Set up Comms Control Room | 8 days | 2024 January 16 8:00 AM | 2024 January 25 5:00 PM | 54 | 0 | 3 | 2024 January 08 8:00 AM | 2024 January 17 5:00 PM | 8 days | 6d | 6d | 0 | 7680 | 7680 | 0 | 0 | 7680
Security Systems | 25 days | 2024 January 26 8:00 AM | 2024 February 29 5:00 PM |  | 0 | 3 | 2024 January 18 8:00 AM | 2024 February 21 5:00 PM | 25 days | 6d | 6d | 0 | 19920 | 19920 | 0 | 0 | 19920
Install Security Cameras | 10 days | 2024 January 26 8:00 AM | 2024 February 08 5:00 PM | 55 | 0 | 3 | 2024 January 18 8:00 AM | 2024 January 31 5:00 PM | 10 days | 6d | 6d | 0 | 12800 | 12800 | 0 | 0 | 12800
Install Fire Alarms | 8 days | 2024 February 09 8:00 AM | 2024 February 20 5:00 PM | 57 | 0 | 3 | 2024 February 01 8:00 AM | 2024 February 12 5:00 PM | 8 days | 6d | 6d | 0 | 3200 | 3200 | 0 | 0 | 3200
Install Secure access on doors | 7 days | 2024 February 21 8:00 AM | 2024 February 29 5:00 PM | 58 | 0 | 3 | 2024 February 13 8:00 AM | 2024 February 21 5:00 PM | 7 days | 6d | 6d | 0 | 3920 | 3920 | 0 | 0 | 3920
Configuration and customization | 0 days | 2024 February 29 5:00 PM | 2024 February 29 5:00 PM | 59 | 0 | 3 | 2024 February 21 5:00 PM | 2024 February 21 5:00 PM | 0 days | 6d | 6d | 0 | 0 | 0 | 0 | 0 | 0
Ambulance Station | 45 days | 2023 June 01 8:00 AM | 2023 August 02 5:00 PM |  | 1 | 0 | 2023 June 01 8:00 AM | 2023 July 25 5:00 PM | 39 days | 0d | 6d | 0 | 25960 | 21600 | 4360 | 24960 | 1000
Ambulance Parking | 15 days | 2023 June 01 8:00 AM | 2023 June 21 5:00 PM |  | 1 | 0 | 2023 June 01 8:00 AM | 2023 June 19 5:00 PM | 13 days | 0d | 2d | 0 | 13000 | 10400.000000000002 | 2599.9999999999986 | 12000 | 1000
Paramedic Station | 14 days | 2023 June 22 8:00 AM | 2023 July 11 5:00 PM | 62 | 1 | 0 | 2023 June 20 8:00 AM | 2023 July 05 5:00 PM | 12 days | 2d | 4d | 0 | 7840 | 6720 | 1120 | 7840 | 0
Stores for Ambulance Provisions | 16 days | 2023 July 12 8:00 AM | 2023 August 02 5:00 PM | 63 | 1 | 0 | 2023 July 06 8:00 AM | 2023 July 25 5:00 PM | 14 days | 4d | 6d | 0 | 5120.0000000000009 | 4480 | 640.00000000000057 | 5120.0000000000009 | 0
Signages | 23 days | 2024 March 01 8:00 AM | 2024 April 02 5:00 PM |  | 0 | 3 | 2024 February 22 8:00 AM | 2024 March 25 5:00 PM | 23 days | 6d | 6d | 0 | 28000 | 28000 | 0 | 0 | 28000
Indoor Signages | 9 days | 2024 March 01 8:00 AM | 2024 March 13 5:00 PM |  | 0 | 3 | 2024 February 22 8:00 AM | 2024 March 05 5:00 PM | 9 days | 6d | 6d | 0 | 4000 | 4000 | 0 | 0 | 4000
Install Indoor Signages | 5 days | 2024 March 01 8:00 AM | 2024 March 07 5:00 PM | 43,1,61,29 | 0 | 3 | 2024 February 22 8:00 AM | 2024 February 28 5:00 PM | 5 days | 6d | 6d | 0 | 1600 | 1600 | 0 | 0 | 1600
Power Indoor Signages | 4 days | 2024 March 08 8:00 AM | 2024 March 13 5:00 PM | 67 | 0 | 3 | 2024 February 29 8:00 AM | 2024 March 05 5:00 PM | 4 days | 6d | 6d | 0 | 2400.0000000000005 | 2400.0000000000005 | 0 | 0 | 2400.0000000000005
Outdoor Signages | 14 days | 2024 March 14 8:00 AM | 2024 April 02 5:00 PM |  | 0 | 3 | 2024 March 06 8:00 AM | 2024 March 25 5:00 PM | 14 days | 6d | 6d | 0 | 24000 | 24000 | 0 | 0 | 24000
Install Outdoor Signages | 7 days | 2024 March 14 8:00 AM | 2024 March 22 5:00 PM | 68 | 0 | 3 | 2024 March 06 8:00 AM | 2024 March 14 5:00 PM | 7 days | 6d | 6d | 0 | 8960 | 8960 | 0 | 0 | 8960
Power Outdoor Signages | 7 days | 2024 March 25 8:00 AM | 2024 April 02 5:00 PM | 70 | 0 | 3 | 2024 March 15 8:00 AM | 2024 March 25 5:00 PM | 7 days | 6d | 6d | 0 | 15040 | 15040 | 0 | 0 | 15040
Detail report | 0 days | 2024 April 02 5:00 PM | 2024 April 02 5:00 PM | 71 | 0 | 3 | 2024 March 25 5:00 PM | 2024 March 25 5:00 PM | 0 days | 6d | 6d | 0 | 0 | 0 | 0 | 0 | 0

## Resource_Table1
Name | Type | Material_Label | Initials | Group_Name | Max_Units | Standard_Rate | Overtime_Rate | Cost_Per_Use | Accrue_At | Base_Calendar | Cost_Variance
Project Manager | Work |  | P | emp | 75% | $150.00/h | $0.00/h | 0 | Prorated | Standard
Site Superintendent | Work |  | S | emp | 100% | $100.00/h | $0.00/h | 0 | Prorated | Standard
General Labourer | Work |  | G | emp | 1,000% | $40.00/h | $0.00/h | 0 | Prorated | Standard
ABC Plumbing | Cost |  | A | sub |  |  |  | 0 | End
DEF HVAC | Cost |  | D | sub |  |  |  | 0 | End
GHI Electrical | Cost |  | G | sub |  |  |  | 0 | End
Drywall | Material | sq.ft | D | sup |  | $10.00 |  | 0 | Start
Nikesh | Work |  | N | emp | 100% | $75.00/h | $0.00/h | 0 | Prorated | Standard
Pradip | Work |  | P | emp | 100% | $70.00/h | $0.00/h | 0 | Prorated | Standard
Rojohn | Work |  | R | emp | 100% | $75.00/h | $0.00/h | 0 | Prorated | Standard
Maurvi | Work |  | M | emp | 100% | $75.00/h | $0.00/h | 0 | Prorated | Standard
Paulina | Work |  | P | emp | 100% | $70.00/h | $0.00/h | 0 | Prorated | Standard
Carpenter | Work |  | C | emp | 1,000% | $50.00/h | $0.00/h | 0 | Prorated | Standard
Electrician | Work |  | E | emp | 1,000% | $50.00/h | $0.00/h | 0 | Prorated | Standard
Network administrator | Work |  | N |  | 200% | $100.00/h | $0.00/h | 0 | Prorated | Standard
System administrator | Work |  | S |  | 200% | $120.00/h | $0.00/h | 0 | Prorated | Standard
Technician | Work |  | T |  | 1,000% | $70.00/h | $0.00/h | 0 | Prorated | Standard
Licenses | Material |  | L |  |  | $1,000.00 |  | 0 | Start
OS software | Material |  | O |  |  | $1,200.00 |  | 0 | Start

## Assignment_Table1
Task_Name | Resource_Name | Percent_Work_Complete | Scheduled_Work | Units | Cost_Variance
Wards | Project Manager | 0.25 | 760h | 50%
Create Patient Triage Station | General Labourer | 1 | 0h | 100%
Create Patient Triage Station | Pradip | 1 | 112h | 100%
Create Patient Triage Station | ABC Plumbing | 0
Create Patient Triage Station | Carpenter | 1 | 0h | 200%
Create Patient Triage Station | DEF HVAC | 0
Create Patient Triage Station | Drywall | 1 | 300 sq.ft | 300 sq.ft
Create Patient Triage Station | Electrician | 1 | 224h | 200%
Create Patient Triage Station | GHI Electrical | 0
Set-up Ward | Pradip | 1 | 96h | 100%
Set-up Ward | General Labourer | 1 | 0h | 100%
Set-up Ward | ABC Plumbing | 0
Set-up Ward | Carpenter | 1 | 0h | 400%
Set-up Ward | DEF HVAC | 0
Set-up Ward | Drywall | 1 | 300 sq.ft | 300 sq.ft
Set-up Ward | Electrician | 1 | 480h | 500%
Set-up Ward | GHI Electrical | 0
Set-up Nurses Station | Pradip | 1 | 0h | 100%
Set-up Nurses Station | General Labourer | 1 | 88h | 100%
Furnish Ward | Carpenter | 1 | 72h | 100%
Furnish Ward | ABC Plumbing | 0
Furnish Ward | DEF HVAC | 0
Furnish Ward | Drywall | 1 | 100 sq.ft | 100 sq.ft
Set-up Ward | Rojohn | 5.0000000000000003E-2 | 144h | 100%
Set-up Ward | ABC Plumbing | 0
Set-up Ward | DEF HVAC | 0
Set-up Nurses Station | Site Superintendent | 0 | 80h | 100%
Furnish Ward | Carpenter | 0 | 40h | 100%
Set-up Ward | Paulina | 0 | 96h | 100%
Set-up Ward | General Labourer | 0 | 4.8h | 100%
Set-up Nurses Station | General Labourer | 0 | 80h | 100%
Furnish Ward | Carpenter | 0 | 48h | 100%
Set-up Ward | Rojohn | 0 | 96h | 100%
Set-up Ward | General Labourer | 0 | 96h | 100%
Set-up Nurses Station | General Labourer | 0 | 80h | 100%
Furnish Ward | Carpenter | 0 | 64h | 100%
Set-up Ward | General Labourer | 0 | 96h | 100%
Set-up Ward | Maurvi | 0 | 96h | 100%
Set-up Nurses Station | Paulina | 0 | 72h | 100%
Set-up Nurses Station | General Labourer | 0 | 72h | 100%
Furnish Ward | Carpenter | 0 | 48h | 100%
Set-up Ward | Rojohn | 0 | 96h | 100%
Set-up Nurses Station | General Labourer | 0 | 64h | 100%
Furnish Ward | Carpenter | 0 | 48h | 100%
Furnish Ward | General Labourer | 0 | 48h | 100%
Set up Room | Nikesh | 1 | 128h | 100%
Set up Room | General Labourer | 1 | 128h | 100%
Install Equipment | General Labourer | 1 | 112h | 100%
Set up Room | Pradip | 1 | 120h | 100%
Install Equipment | General Labourer | 1 | 96h | 100%
Set up Room | Drywall | 0 | 200 sq.ft | 200 sq.ft
Set up Room | ABC Plumbing | 0
Install Equipment | Electrician | 0 | 72h | 100%
Install Equipment | General Labourer | 0 | 72h | 100%
Set up Room | Maurvi | 0 | 96h | 100%
Install Equipment | Electrician | 0 | 80h | 100%
Install Equipment | General Labourer | 0 | 80h | 100%
Install Network | Network administrator | 0 | 96h | 100%
Install Network | Licenses | 0 | 2 | 2
Install Hardware | Technician | 0 | 80h | 100%
Install Software | Technician | 0 | 40h | 100%
Install Software | OS software | 0 | 2 | 2
Install Computers | System administrator | 0 | 80h | 100%
Install Computers | Technician | 0 | 80h | 100%
Install OS | Technician | 0 | 32h | 100%
Install OS | Licenses | 0 | 3 | 3
Install OS | OS software | 0 | 5 | 5
Install telephones | Technician | 0 | 64h | 100%
Install Public Address system | Technician | 0 | 72h | 100%
Connect phones | Technician | 0 | 56h | 100%
Set up Comms Control Room | Electrician | 0 | 64h | 100%
Set up Comms Control Room | Technician | 0 | 64h | 100%
Install Security Cameras | Electrician | 0 | 80h | 100%
Install Security Cameras | General Labourer | 0 | 80h | 100%
Install Security Cameras | Technician | 0 | 80h | 100%
Install Fire Alarms | Electrician | 0 | 64h | 100%
Install Secure access on doors | Technician | 0 | 56h | 100%
Ambulance Parking | Site Superintendent | 1 | 120h | 100%
Ambulance Parking | GHI Electrical | 0
Paramedic Station | Paulina | 1 | 112h | 100%
Paramedic Station | General Labourer | 1 | 0h | 200%
Stores for Ambulance Provisions | General Labourer | 1 | 128h | 100%
Install Indoor Signages | General Labourer | 0 | 40h | 100%
Install Indoor Signages | GHI Electrical | 0
Power Indoor Signages | Rojohn | 0 | 32h | 100%
Power Indoor Signages | GHI Electrical | 0
Install Outdoor Signages | Pradip | 0 | 56h | 100%
Install Outdoor Signages | General Labourer | 0 | 56h | 100%
Install Outdoor Signages | Electrician | 0 | 56h | 100%
Power Outdoor Signages | Electrician | 0 | 56h | 100%
Power Outdoor Signages | GHI Electrical | 0
Power Outdoor Signages | General Labourer | 0 | 56h | 100%

## Earned Value Report
EARNED VALUE OVER TIME
The project’s earned value based on the status date. If actual cost (ACWP) is higher than earned value (BCWP), then the project is over budget. If planned value (BCWS) is higher than earned value, then the project is behind schedule.
VARIANCE OVER TIME
Cost and schedule variances for the project based on status date. If CV is negative then, the project is over budget. If SV is positive then the project is behind schedule.
INDICES OVER TIME
Cost and schedule performance indices for the project based on status date. The greater the performance index, the more on schedule and cost saving the project.
EARNED VALUE

## Resource cost report
Resource Cost Overview
COST STATUS
COST DISTRIBUTION
COST DETAILS
Cost status for work resources.
How costs are spread out amongst different resource types.
Cost details for all work resources.

## Task Report
Critical Tasks
A task is critical if there is no room in the schedule for it to slip.

## Cost Variance
Cash Flow