## Group Details
EPM 1173_4/Spring 2023
Group 7
Name | Student ID
Nikesh Pathak | c0906596
Maurvi Shah | c0897184
Pradip Shrestha | c0899894
Paulina Jaramillo | c0897079
Rojohn Shrestha | c0898077

## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Auto Scheduled | Wards | 183 days | 2023 June 01 8:00 AM | 2024 February 12 5:00 PM |  | 1
2 | Yes | Auto Scheduled | Emergency Ward | 39 days | 2023 June 01 8:00 AM | 2023 July 25 5:00 PM |  | 2
3 | Yes | Auto Scheduled | Create Patient Triage Station | 12 days | 2023 June 01 8:00 AM | 2023 June 16 5:00 PM |  | 3
4 | Yes | Auto Scheduled | Set-up Ward | 10 days | 2023 June 16 5:00 PM | 2023 June 30 5:00 PM | 3 | 3
5 | Yes | Auto Scheduled | Set-up Nurses Station | 9 days | 2023 June 30 5:00 PM | 2023 July 13 5:00 PM | 4 | 3
6 | Yes | Auto Scheduled | Furnish Ward | 8 days | 2023 July 14 8:00 AM | 2023 July 25 5:00 PM | 5 | 3 | ...
7 | Yes | Auto Scheduled | Inspection approved | 0 days | 2023 July 25 5:00 PM | 2023 July 25 5:00 PM | 6 | 3
8 | Yes | Auto Scheduled | ICU | 33 days | 2023 July 26 8:00 AM | 2023 September 08 5:00 PM |  | 2
9 | Yes | Auto Scheduled | Set-up Ward | 18 days | 2023 July 26 8:00 AM | 2023 August 18 5:00 PM | 7 | 3
10 | Yes | Auto Scheduled | Set-up Nurses Station | 10 days | 2023 August 21 8:00 AM | 2023 September 01 5:00 PM | 9 | 3
11 | Yes | Auto Scheduled | Furnish Ward | 5 days | 2023 September 04 8:00 AM | 2023 September 08 5:00 PM | 10 | 3
12 | Yes | Auto Scheduled | Medicine Ward | 28 days | 2023 September 11 8:00 AM | 2023 October 18 5:00 PM |  | 2
13 | Yes | Auto Scheduled | Set-up Ward | 12 days | 2023 September 11 8:00 AM | 2023 September 26 5:00 PM | 11 | 3
14 | Yes | Auto Scheduled | Set-up Nurses Station | 10 days | 2023 September 27 8:00 AM | 2023 October 10 5:00 PM | 13 | 3
15 | Yes | Auto Scheduled | Furnish Ward | 6 days | 2023 October 11 8:00 AM | 2023 October 18 5:00 PM | 14 | 3
16 | Yes | Auto Scheduled | General Ward | 30 days | 2023 October 19 8:00 AM | 2023 November 29 5:00 PM |  | 2
17 | Yes | Auto Scheduled | Set-up Ward | 12 days | 2023 October 19 8:00 AM | 2023 November 03 5:00 PM | 15 | 3
18 | Yes | Auto Scheduled | Set-up Nurses Station | 10 days | 2023 November 06 8:00 AM | 2023 November 17 5:00 PM | 17 | 3
19 | Yes | Auto Scheduled | Furnish Ward | 8 days | 2023 November 20 8:00 AM | 2023 November 29 5:00 PM | 18 | 3
20 | Yes | Auto Scheduled | Orthopedic Ward | 27 days | 2023 November 30 8:00 AM | 2024 January 05 5:00 PM |  | 2
21 | Yes | Auto Scheduled | Set-up Ward | 12 days | 2023 November 30 8:00 AM | 2023 December 15 5:00 PM | 19 | 3
22 | Yes | Auto Scheduled | Set-up Nurses Station | 9 days | 2023 December 18 8:00 AM | 2023 December 28 5:00 PM | 21 | 3
23 | Yes | Auto Scheduled | Furnish Ward | 6 days | 2023 December 29 8:00 AM | 2024 January 05 5:00 PM | 22 | 3
24 | Yes | Auto Scheduled | Paediatric Ward | 26 days | 2024 January 08 8:00 AM | 2024 February 12 5:00 PM |  | 2
25 | Yes | Auto Scheduled | Set-up Ward | 12 days | 2024 January 08 8:00 AM | 2024 January 23 5:00 PM | 23 | 3
26 | Yes | Auto Scheduled | Set-up Nurses Station | 8 days | 2024 January 24 8:00 AM | 2024 February 02 5:00 PM | 25 | 3
27 | Yes | Auto Scheduled | Furnish Ward | 6 days | 2024 February 05 8:00 AM | 2024 February 12 5:00 PM | 26 | 3
28 | Yes | Auto Scheduled | Final Inspection | 0 days | 2024 February 12 5:00 PM | 2024 February 12 5:00 PM | 27 | 2
29 | Yes | Auto Scheduled | Speciality Rooms | 92 days | 2023 June 01 8:00 AM | 2023 October 06 5:00 PM |  | 1
30 | Yes | Auto Scheduled | X-ray Room | 26 days | 2023 June 01 8:00 AM | 2023 July 06 5:00 PM |  | 2
31 | Yes | Auto Scheduled | Set up Room | 14 days | 2023 June 01 8:00 AM | 2023 June 20 5:00 PM |  | 3
32 | Yes | Auto Scheduled | Install Equipment | 12 days | 2023 June 21 8:00 AM | 2023 July 06 5:00 PM | 31 | 3
33 | Yes | Auto Scheduled | CT Scan Room | 25 days | 2023 July 07 8:00 AM | 2023 August 10 5:00 PM |  | 2
34 | Yes | Auto Scheduled | Set up Room | 14 days | 2023 July 07 8:00 AM | 2023 July 26 5:00 PM | 32 | 3
35 | Yes | Auto Scheduled | Install Equipment | 11 days | 2023 July 27 8:00 AM | 2023 August 10 5:00 PM | 34 | 3
36 | Yes | Auto Scheduled | Blood Works Lab | 19 days | 2023 August 11 8:00 AM | 2023 September 06 5:00 PM |  | 2
37 | Yes | Auto Scheduled | Set up Room | 10 days | 2023 August 11 8:00 AM | 2023 August 24 5:00 PM | 35 | 3
38 | Yes | Auto Scheduled | Install Equipment | 9 days | 2023 August 25 8:00 AM | 2023 September 06 5:00 PM | 37 | 3
39 | Yes | Auto Scheduled | ECG | 22 days | 2023 September 07 8:00 AM | 2023 October 06 5:00 PM |  | 2
40 | Yes | Auto Scheduled | Set up Room | 12 days | 2023 September 07 8:00 AM | 2023 September 22 5:00 PM | 38 | 3
41 | Yes | Auto Scheduled | Install Equipment | 10 days | 2023 September 25 8:00 AM | 2023 October 06 5:00 PM | 40 | 3
42 | Yes | Auto Scheduled | Final inspection | 0 days | 2023 October 06 5:00 PM | 2023 October 06 5:00 PM | 41 | 3
43 | Yes | Auto Scheduled | IT Systems | 98 days | 2023 October 09 8:00 AM | 2024 February 21 5:00 PM |  | 1
44 | Yes | Auto Scheduled | Server room + Networking | 27 days | 2023 October 09 8:00 AM | 2023 November 14 5:00 PM |  | 2
45 | Yes | Auto Scheduled | Install Network | 12 days | 2023 October 09 8:00 AM | 2023 October 24 5:00 PM | 41 | 3
46 | Yes | Auto Scheduled | Install Hardware | 10 days | 2023 October 25 8:00 AM | 2023 November 07 5:00 PM | 45 | 3
47 | Yes | Auto Scheduled | Install Software | 5 days | 2023 November 08 8:00 AM | 2023 November 14 5:00 PM | 46 | 3
48 | Yes | Auto Scheduled | Computers | 14 days | 2023 November 15 8:00 AM | 2023 December 04 5:00 PM |  | 2
49 | Yes | Auto Scheduled | Install Computers | 10 days | 2023 November 15 8:00 AM | 2023 November 28 5:00 PM | 47 | 3
50 | Yes | Auto Scheduled | Install OS | 4 days | 2023 November 29 8:00 AM | 2023 December 04 5:00 PM | 49 | 3
51 | Yes | Auto Scheduled | Communications Systems | 32 days | 2023 December 05 8:00 AM | 2024 January 17 5:00 PM |  | 2
52 | Yes | Auto Scheduled | Install telephones | 8 days | 2023 December 05 8:00 AM | 2023 December 14 5:00 PM | 50 | 3
53 | Yes | Auto Scheduled | Install Public Address system | 9 days | 2023 December 15 8:00 AM | 2023 December 27 5:00 PM | 52 | 3
54 | Yes | Auto Scheduled | Connect phones | 7 days | 2023 December 28 8:00 AM | 2024 January 05 5:00 PM | 53 | 3
55 | Yes | Auto Scheduled | Set up Comms Control Room | 8 days | 2024 January 08 8:00 AM | 2024 January 17 5:00 PM | 54 | 3
56 | Yes | Auto Scheduled | Security Systems | 25 days | 2024 January 18 8:00 AM | 2024 February 21 5:00 PM |  | 2
57 | Yes | Auto Scheduled | Install Security Cameras | 10 days | 2024 January 18 8:00 AM | 2024 January 31 5:00 PM | 55 | 3
58 | Yes | Auto Scheduled | Install Fire Alarms | 8 days | 2024 February 01 8:00 AM | 2024 February 12 5:00 PM | 57 | 3
59 | Yes | Auto Scheduled | Install Secure access on doors | 7 days | 2024 February 13 8:00 AM | 2024 February 21 5:00 PM | 58 | 3
60 | Yes | Auto Scheduled | Configuration and customization | 0 days | 2024 February 21 5:00 PM | 2024 February 21 5:00 PM | 59 | 3
61 | Yes | Auto Scheduled | Ambulance Station | 39 days | 2023 June 01 8:00 AM | 2023 July 25 5:00 PM |  | 1
62 | Yes | Auto Scheduled | Ambulance Parking | 13 days | 2023 June 01 8:00 AM | 2023 June 19 5:00 PM |  | 2
63 | Yes | Auto Scheduled | Paramedic Station | 12 days | 2023 June 20 8:00 AM | 2023 July 05 5:00 PM | 62 | 2
64 | Yes | Auto Scheduled | Stores for Ambulance Provisions | 14 days | 2023 July 06 8:00 AM | 2023 July 25 5:00 PM | 63 | 2
65 | Yes | Auto Scheduled | Signages | 23 days | 2024 February 22 8:00 AM | 2024 March 25 5:00 PM |  | 1
66 | Yes | Auto Scheduled | Indoor Signages | 9 days | 2024 February 22 8:00 AM | 2024 March 05 5:00 PM |  | 2
67 | Yes | Auto Scheduled | Install Indoor Signages | 5 days | 2024 February 22 8:00 AM | 2024 February 28 5:00 PM | 43,1,61,29 | 3
68 | Yes | Auto Scheduled | Power Indoor Signages | 4 days | 2024 February 29 8:00 AM | 2024 March 05 5:00 PM | 67 | 3
69 | Yes | Auto Scheduled | Outdoor Signages | 14 days | 2024 March 06 8:00 AM | 2024 March 25 5:00 PM |  | 2
70 | Yes | Auto Scheduled | Install Outdoor Signages | 7 days | 2024 March 06 8:00 AM | 2024 March 14 5:00 PM | 68 | 3
71 | Yes | Auto Scheduled | Power Outdoor Signages | 7 days | 2024 March 15 8:00 AM | 2024 March 25 5:00 PM | 70 | 3
72 | Yes | Auto Scheduled | Detail report | 0 days | 2024 March 25 5:00 PM | 2024 March 25 5:00 PM | 71 | 3

## Resource_Table
ID | Name | Initials | Type | Material Label | Group | Email Address | User Logon Account | Max Units | Standard Rate | Cost Per Use | Notes
1 | Project Manager | P | Work |  | emp |  |  | 75% | $150.00/h | 0
2 | Site Superintendent | S | Work |  | emp |  |  | 100% | $100.00/h | 0
3 | General Labourer | G | Work |  | emp |  |  | 500% | $40.00/h | 0
4 | ABC Plumbing | A | Cost |  | sub |  |  |  |  | 0
5 | DEF HVAC | D | Cost |  | sub |  |  |  |  | 0
6 | GHI Electrical | G | Cost |  | sub |  |  |  |  | 0
7 | Drywall | D | Material | sq.ft | sup |  |  |  | $10.00 | 0
8 | Nikesh | N | Work |  | emp |  |  | 100% | $75.00/h | 0
9 | Pradip | P | Work |  | emp |  |  | 100% | $70.00/h | 0
10 | Rojohn | R | Work |  | emp |  |  | 100% | $75.00/h | 0
11 | Maurvi | M | Work |  | emp |  |  | 100% | $75.00/h | 0
12 | Paulina | P | Work |  | emp |  |  | 100% | $70.00/h | 0
13 | Carpenter | C | Work |  | emp |  |  | 500% | $50.00/h | 0
14 | Electrician | E | Work |  | emp |  |  | 300% | $50.00/h | 0
15 | Network administrator | N | Work |  |  |  |  | 100% | $100.00/h | 0
16 | System administrator | S | Work |  |  |  |  | 100% | $120.00/h | 0
17 | Technician | T | Work |  |  |  |  | 400% | $70.00/h | 0
18 | Licenses | L | Material | [5 empty] | $1,000.00 | 0
19 | OS software | O | Material | [5 empty] | $1,200.00 | 0

## Assignment_Table
Task Name | Resource Name | % Work Complete | Work | Units
Wards | Project Manager | 0 | 732h | 50%
Create Patient Triage Station | General Labourer | 0 | 0h | 100%
Create Patient Triage Station | Pradip | 0 | 96h | 100%
Set-up Ward | PradiP | 0 | 80h | 100%
Set-up Ward | General Labourer | 0 | 0h | 100%
Set-up Nurses Station | Pradip | 0 | 0h | 100%
Set-up Nurses Station | General Labourer | 0 | 72h | 100%
Furnish Ward | Carpenter | 0 | 64h | 100%
Set-up Ward | Rojohn | 0 | 144h | 100%
Set-up Nurses Station | Site Superintendent | 0 | 80h | 100%
Furnish Ward | Carpenter | 0 | 40h | 100%
Set-up Ward | Paulina | 0 | 96h | 100%
Set-up Ward | General Labourer | 0 | 4.8h | 100%
Set-up Nurses Station | General Labourer | 0 | 80h | 100%
Furnish Ward | Carpenter | 0 | 48h | 100%
Set-up Ward | Rojohn | 0 | 96h | 100%
Set-up Ward | General Labourer | 0 | 96h | 100%
Set-up Nurses Station | General Labourer | 0 | 80h | 100%
Furnish Ward | Carpenter | 0 | 64h | 100%
Set-up Ward | General Labourer | 0 | 96h | 100%
Set-up Ward | Maurvi | 0 | 96h | 100%
Set-up Nurses Station | Paulina | 0 | 72h | 100%
Set-up Nurses Station | General Labourer | 0 | 72h | 100%
Furnish Ward | Carpenter | 0 | 48h | 100%
Set-up Ward | Rojohn | 0 | 96h | 100%
Set-up Nurses Station | General Labourer | 0 | 64h | 100%
Furnish Ward | Carpenter | 0 | 48h | 100%
Furnish Ward | General Labourer | 0 | 48h | 100%
Set up Room | Nikesh | 0 | 112h | 100%
Set up Room | General Labourer | 0 | 112h | 100%
Install Equipment | General Labourer | 0 | 96h | 100%
Set up Room | Pradip | 0 | 112h | 100%
Install Equipment | General Labourer | 0 | 88h | 100%
Set up Room | Drywall | 0 | 200 sq.ft | 200 sq.ft
Set up Room | ABC Plumbing | 0
Install Equipment | Electrician | 0 | 72h | 100%
Install Equipment | General Labourer | 0 | 72h | 100%
Set up Room | Maurvi | 0 | 96h | 100%
Install Equipment | Electrician | 0 | 80h | 100%
Install Equipment | General Labourer | 0 | 80h | 100%
Install Network | Network administrator | 0 | 96h | 100%
Install Network | Licenses | 0 | 2 | 2
Install Hardware | Technician | 0 | 80h | 100%
Install Software | Technician | 0 | 40h | 100%
Install Software | OS software | 0 | 2 | 2
Install Computers | System administrator | 0 | 80h | 100%
Install Computers | Technician | 0 | 80h | 100%
Install OS | Technician | 0 | 32h | 100%
Install OS | Licenses | 0 | 3 | 3
Install OS | OS software | 0 | 5 | 5
Install telephones | Technician | 0 | 64h | 100%
Install Public Address system | Technician | 0 | 72h | 100%
Connect phones | Technician | 0 | 56h | 100%
Set up Comms Control Room | Electrician | 0 | 64h | 100%
Set up Comms Control Room | Technician | 0 | 64h | 100%
Install Security Cameras | Electrician | 0 | 80h | 100%
Install Security Cameras | General Labourer | 0 | 80h | 100%
Install Security Cameras | Technician | 0 | 80h | 100%
Install Fire Alarms | Electrician | 0 | 64h | 100%
Install Secure access on doors | Technician | 0 | 56h | 100%
Ambulance Parking | Site Superintendent | 0 | 104h | 100%
Paramedic Station | Paulina | 0 | 96h | 100%
Stores for Ambulance Provisions | General Labourer | 0 | 112h | 100%
Install Indoor Signages | General Labourer | 0 | 40h | 100%
Install Indoor Signages | GHI Electrical | 0
Power Indoor Signages | Rojohn | 0 | 32h | 100%
Power Indoor Signages | GHI Electrical | 0
Install Outdoor Signages | Pradip | 0 | 56h | 100%
Install Outdoor Signages | General Labourer | 0 | 56h | 100%
Install Outdoor Signages | Electrician | 0 | 56h | 100%
Power Outdoor Signages | Electrician | 0 | 56h | 100%
Power Outdoor Signages | GHI Electrical | 0
Power Outdoor Signages | General Labourer | 0 | 56h | 100%